## Sheet2
Keith Kelliher t/a Kelliher and Associates take no responsibility in any way whatsoever for the use, or any reliance in whatever form of the attached template
It is the responsibility of the user to ensure they get the correct advise as to the use, the dates, the format and the likes as is required

## CCA Timetable
Commencement Date | 2017-11-03 | days |  | 5 | days | 21 | 30
|  | Period in which Payment Claim notice must be submitted |  |  | Final Date for Response to be Received |  | Payment Due Date
|  | earliest |  | latest
Payment Claim Date Month 1 | 2017-12-03 | 2017-12-03 | and | 2017-12-08 | 2017-12-24 |  | 2018-01-02
Payment Claim Date Month 2 | 2018-01-02 | 2018-01-02 | and | 2018-01-07 | 2018-01-23 |  | 2018-02-01
Payment Claim Date Month 3 | 2018-02-01 | 2018-02-01 | and | 2018-02-06 | 2018-02-22 |  | 2018-03-03
Payment Claim Date Month 4 | 2018-03-03 | 2018-03-03 | and | 2018-03-08 | 2018-03-24 |  | 2018-04-02
Payment Claim Date Month 5 | 2018-04-02 | 2018-04-02 | and | 2018-04-07 | 2018-04-23 |  | 2018-05-02
Payment Claim Date Month 6 | 2018-05-02 | 2018-05-02 | and | 2018-05-07 | 2018-05-23 |  | 2018-06-01
Payment Claim Date Month 7 | 2018-06-01 | 2018-06-01 | and | 2018-06-06 | 2018-06-22 |  | 2018-07-01
Payment Claim Date Month 8 | 2018-07-01 | 2018-07-01 | and | 2018-07-06 | 2018-07-22 |  | 2018-07-31
Substantial Completion (SC) | date of sc | date of sc | and | date of sc plus 5 | date of sc plus 21 |  | date of sc plus 30
Final Completion (FC) | Date
Last Payment Claim Date | FC date plus 30 | FC date plus 30 | and | FC Date plus 35 | FC date plus 51 |  | FC date plus 60
currently unknown what happens between substantial completion and final completion
if this period is less than 30 days, if more then another payment claim date applies but the final payment claim date is done on date of substantial completion